BEST PRACTICES & CHECKLIST
IMPLEMENTASI SIM PENJAMINAN MUTU

# PRE-IMPLEMENTATION CHECKLIST

## 1. Organizational Readiness

☐ Commitment letter dari pimpinan institusi

☐ Steering committee sudah dibentuk

☐ Budget telah disetujui dan dialokasikan

☐ Project charter telah ditandatangani

☐ Stakeholder analysis telah dilakukan

☐ Change management strategy telah disiapkan

☐ Communication plan telah dibuat

☐ Risk register telah disusun

## 2. Technical Readiness

☐ Server/hosting telah dipilih

☐ Domain dan SSL certificate ready

☐ Development environment setup

☐ Version control repository (Git) ready

☐ CI/CD pipeline configured

☐ Database server ready

☐ Backup strategy defined

☐ Security requirements documented

☐ Network infrastructure assessed

## 3. Team Readiness

☐ Project manager assigned

☐ Business analyst identified

☐ Developer team formed

☐ QA tester assigned

☐ DevOps engineer ready

☐ UI/UX designer available

☐ Key users identified per unit

☐ Training plan prepared

☐ Team roles & responsibilities documented

## 4. Data Readiness

☐ Current data inventory completed

☐ Data quality assessment done

☐ Data cleansing plan prepared

☐ Master data defined

☐ Data migration strategy ready

☐ Data ownership assigned

☐ Data governance policy documented

# DEVELOPMENT BEST PRACTICES

## 1. Code Quality

✓ Gunakan PSR-12 coding standard untuk PHP

✓ Implement code review untuk setiap pull request

✓ Maintain test coverage minimal 70%

✓ Use meaningful variable dan function names

✓ Write self-documenting code dengan comments yang relevan

✓ Follow SOLID principles

✓ Avoid code duplication (DRY principle)

✓ Regular code refactoring

## 2. Database Management

✓ Always use database migrations untuk schema changes

✓ Implement database indexing untuk performance

✓ Use soft deletes untuk data penting

✓ Regular database backup (automated)

✓ Optimize queries dengan explain analyze

✓ Implement database connection pooling

✓ Use transactions untuk data consistency

✓ Regular vacuum/optimize tables

## 3. API Development

✓ Follow RESTful conventions

✓ Implement proper HTTP status codes

✓ Use API versioning (v1, v2)

✓ Comprehensive API documentation (Swagger/OpenAPI)

✓ Implement rate limiting

✓ Use pagination untuk large datasets

✓ Implement proper error handling

✓ API response caching where applicable

✓ Use JWT tokens dengan proper expiry

## 4. Security Practices

✓ Never store passwords in plain text (use bcrypt)

✓ Implement input validation & sanitization

✓ Use parameterized queries (prevent SQL injection)

✓ Implement CSRF protection

✓ Use HTTPS everywhere

✓ Implement proper session management

✓ Regular security audits & penetration testing

✓ Keep dependencies updated

✓ Implement proper logging (no sensitive data)

✓ Use security headers (CSP, HSTS, etc.)

✓ Implement rate limiting untuk prevent brute force

✓ Regular vulnerability scanning

## 5. Performance Optimization

✓ Implement caching strategy (Redis)

✓ Use eager loading untuk prevent N+1 queries

✓ Optimize images (compression, lazy loading)

✓ Implement CDN untuk static assets

✓ Database query optimization

✓ Use queue untuk heavy tasks

✓ Implement pagination

✓ Minify CSS & JavaScript

✓ Enable gzip compression

✓ Regular performance monitoring

# TESTING STRATEGY

## 1. Unit Testing

✓ Test individual functions/methods

✓ Coverage target: > 70%

✓ Use PHPUnit untuk Laravel

✓ Mock external dependencies

✓ Run tests automatically dalam CI/CD

## 2. Integration Testing

✓ Test interaction between modules

✓ Test API endpoints

✓ Test database operations

✓ Test external integrations (SIAKAD, etc.)

## 3. User Acceptance Testing (UAT)

✓ Involve actual end users

✓ Test with real-world scenarios

✓ Document test cases & results

✓ Collect feedback systematically

✓ Sign-off dari key users

## 4. Performance Testing

✓ Load testing (JMeter, k6)

✓ Stress testing

✓ Scalability testing

✓ Monitor server resources

## 5. Security Testing

✓ Penetration testing

✓ Vulnerability scanning

✓ SQL injection testing

✓ XSS testing

✓ Authentication/authorization testing

# DEPLOYMENT CHECKLIST

## Pre-Deployment

☐ All tests passed (unit, integration, UAT)

☐ Code review completed

☐ Security audit done

☐ Performance testing completed

☐ Documentation updated

☐ Database migration scripts ready

☐ Rollback plan prepared

☐ Backup of production data taken

☐ Deployment runbook prepared

☐ Stakeholders notified

## During Deployment

☐ Put maintenance page up

☐ Stop background jobs

☐ Take final backup

☐ Deploy code to production

☐ Run database migrations

☐ Clear caches

☐ Restart services

☐ Run smoke tests

☐ Check logs for errors

☐ Monitor system resources

## Post-Deployment

☐ Remove maintenance page

☐ Verify all critical features working

☐ Check error logs

☐ Monitor performance metrics

☐ Test integrations

☐ Notify stakeholders of successful deployment

☐ Update documentation if needed

☐ Monitor for next 24 hours

☐ Collect user feedback

☐ Document lessons learned

# MONITORING & MAINTENANCE

## 1. What to Monitor

### System Health

• CPU usage

• Memory usage

• Disk space

• Network traffic

• Application response time

• Error rates

• Database connections

• Queue length

### Application Metrics

• Active users

• Page views

• API requests

• Failed logins

• Slow queries

• Exception rates

• File uploads/downloads

• Email delivery rate

## 2. Monitoring Tools (Recommended)

✓ New Relic / Datadog untuk application monitoring

✓ Prometheus + Grafana untuk metrics

✓ ELK Stack untuk log management

✓ Sentry untuk error tracking

✓ Uptime Robot untuk uptime monitoring

✓ Google Analytics untuk user analytics

## 3. Maintenance Schedule

### Daily

• Check error logs

• Monitor system health

• Verify backups

• Check critical alerts

### Weekly

• Review performance metrics

• Check disk space trends

• Update dependency security patches

• Review user feedback

### Monthly

• Full system health check

• Database optimization

• Security audit

• Generate usage reports

• Review & update documentation

### Quarterly

• Disaster recovery drill

• Capacity planning review

• Major updates & upgrades

• Stakeholder review meeting

# COMMON PITFALLS TO AVOID

## 1. Scope Creep

How to Avoid: Define clear requirements, implement change control process, prioritize features using MoSCoW method

## 2. Poor Communication

How to Avoid: Regular standups, sprint reviews, stakeholder meetings, use collaboration tools (Slack, Teams)

## 3. Inadequate Testing

How to Avoid: Invest in automated testing, allocate time for UAT, maintain test coverage

## 4. Ignoring Performance

How to Avoid: Performance testing from early stages, set performance budgets, regular optimization

## 5. Security as Afterthought

How to Avoid: Security by design, regular security audits, security training for team

## 6. No Documentation

How to Avoid: Document as you go, use tools like Swagger for API docs, maintain user manuals

## 7. Lack of Monitoring

How to Avoid: Implement monitoring from day 1, set up alerts, regular review of metrics

## 8. Poor Change Management

How to Avoid: Early user involvement, training programs, phased rollout, support system

## 9. Technical Debt

How to Avoid: Regular refactoring, code reviews, maintain coding standards, allocate time for tech debt

## 10. Single Point of Failure

How to Avoid: Redundancy in critical systems, backup strategies, disaster recovery plan

# QUICK REFERENCE GUIDE

## Laravel Artisan Commands

php artisan serve - Start development server

php artisan migrate - Run database migrations

php artisan db:seed - Seed database

php artisan queue:work - Process queue jobs

php artisan cache:clear - Clear application cache

php artisan config:cache - Cache configuration

php artisan route:list - List all routes

php artisan make:model - Create model

php artisan make:controller - Create controller

php artisan make:migration - Create migration

php artisan test - Run tests

## Git Commands

git status - Check working directory status

git add . - Stage all changes

git commit -m "message" - Commit changes

git push origin branch - Push to remote

git pull origin branch - Pull from remote

git checkout -b branch - Create new branch

git merge branch - Merge branch

git log - View commit history

## Common Issues & Solutions

### Issue: Slow Performance

✓ Enable query logging and check for N+1 queries

✓ Implement eager loading

✓ Add database indexes

✓ Enable caching

✓ Optimize images

### Issue: High Memory Usage

✓ Use chunk() untuk large datasets

✓ Implement pagination

✓ Use generators untuk large file processing

✓ Clear unused objects

✓ Increase PHP memory_limit if needed

### Issue: Session Issues

✓ Check session driver configuration

✓ Clear session storage

✓ Check session lifetime

✓ Verify CSRF tokens

# USEFUL RESOURCES

## Documentation

• Laravel: https://laravel.com/docs

• Vue.js: https://vuejs.org/guide/

• Tailwind CSS: https://tailwindcss.com/docs

• PostgreSQL: https://www.postgresql.org/docs/

• Redis: https://redis.io/docs/

## Learning Resources

• Laracasts: https://laracasts.com

• Vue Mastery: https://www.vuemastery.com

• FreeCodeCamp: https://www.freecodecamp.org

• MDN Web Docs: https://developer.mozilla.org

## Tools & Libraries

• Postman: API testing

• VS Code: Code editor

• TablePlus: Database GUI

• Figma: UI/UX design

• Git: Version control

• Docker: Containerization

## Community

• Laravel.io: Laravel forum

• Stack Overflow: Q&A

• GitHub: Code repository

• Reddit r/laravel: Community discussion

Tips Terakhir: Start small, iterate fast, listen to users, document everything, and never stop learning!

Good luck with your implementation! 🚀